## Cover Sheet
Transport and Main Roads Decision Making Tool
Project
Decision
Analysis undertaken by | Include the teams and leads involved
Date of decision | Specific date or time period
Option selected & details | Brief summary of option, why it was selected and why alternatives were not
Version | Description
1 | Final

## Step 1 Decisions Flow Chart
Sustainable Decision-Making Flow Chart
Note: All issues / decisions that generate a scope change or cost impact greater than 5-10% must be recorded in TMR's Project Scope Change Register and assessed against the Sustainable Decision-Making Flow Chart. If the assessment outcome is 'yes' an MCA must be undertaken. An MCA shall not be undertaken on any directions by the Minister or Project Owner.
Will the decision have a cost impact of greater than 5-10%
No
Yes
Following MCA recommended preferred option to be submitted to PCG for approval. If approved, add to Project Scope Change Register
Does the decision have both an impact on the scope AND either a community impact or potential reputational impact
Yes
No
Yes
Record in TMR's Issues, Decisions and Scope Change Register and undertake MCA in accordance with the Decision-Making Tool Guidance
Yes
Record in TMR's Issues, Decisions and Scope Change Register and undertake MCA in accordance with the Decision Making Tool Guidance document
Following MCA recommended option to be submitted to TMR for approval. If approved, add to Project Scope Change Register
No MCA required

## Step 2 Multi-Criteria Analysis
Transport and Main Roads Decision Making Tool
Decision: | Insert name of decision
Forecast Useful Life of Asset | [# years]
Instructions
Ensure MCA is undertaken in accordance with the below and the Decision Making Tool Guidance Document. Step 1: Customise "Criteria" to be considered in the decision Step 2: Customise "Criteria" weightings and ensure they sum to 100% for each "Aspect" and the Total "Aspect" Column adds to 100% Step 3: Input details for each option's details ensuring the forecast useful life of the asset is considered Step 4: Score criteria per option on a 1 - 5 scale and consider score in relation to forecast asset life 1 = Unacceptable, requires mitigation activity 2 = Below average benefits 3 = Average benefits 4 = Above average benefits 5 = Significant benefits Step 6: Review results and submit preferred option to PCG for approval. If approved, add to Project Scope Change Register Note: Aspect Weightings should be kept consistent across all MCA's ensuring sustainability aspects (non-financial) represent greater than 20% of the overall weighting
Aspect | Criteria | Weightings |  | Option 1 |  | Option 2 |  | Option 3 |  | Option 4
|  |  |  | Description |  | Description |  | Description |  | Description
| Customisable |  | Aspect | Response | Score ( 1-5) | Response | Score (1-5) | Response | Score (1-5) | Response | Score (1-5)
Constructability | Staging | 30% | 20%
| Timing (duration) | 35%
| TTM | 35%
Constructability criteria 4
| Constructability criteria total | 100% |  |  | 0 |  | 0 |  | 0 |  | 0
Environmental | Construction environmental impact (habitat loss, water quality, air quality, noise, vibration) | 35% | 15%
| Operational environmental impact (noise, vibration, air quality, water quality) | 35%
| Impact to cultural heritage | 30%
Environmental criteria 4
Environmental criteria 5
| Environmental criteria total | 100% |  |  | 0 |  | 0 |  | 0 |  | 0
Economic / Financial | Capital expenditure | 35% | 35%
| Operational expenditure | 35%
| Value engineering opportunities | 15%
| Local businesses | 15%
| Economic criteria total | 100% |  |  | 0 |  | 0 |  | 0 |  | 0
Social | Community connectivity | 25% | 15%
| Active transport | 25%
| Construction impacts | 50%
Social criteria 4
| Social criteria total | 100% |  |  | 0 |  | 0 |  | 0 |  | 0
Functionality | Delivery timeframe | 25% | 15%
| Future proofing / adaptability | 25%
| Transport network improvement | 25%
| Planning and permits required | 25%
Functional criteria 5
| Functionality criteria total | 100% |  |  | 0 |  | 0 |  | 0
TOTALS |  |  | 100% |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | 0% |  | 0% |  | 0% |  | 0%