## Sheet1
This calculator is able to convert 'current' dollars using a proposed cash flow and user-defined escalation rates to an expenditure profile in estimated 'out-turn' dollars.
Project No.: | 222/333/444 |  |  | Enter data in green shaded cells
Financial Year | 2020-21 |  | Costs to date (sunk costs) | 2020-21 |  | 2021-22 |  | 2022-23 |  | 2023-24 |  | 2024-25
| Estimated Costs in 'current'* dollars ($,000) |  | Proposed Cash Flow in 'current'* dollars ($,000)
Estimated Cost Component | Base Estimate | Contingency Allowance | Actuals | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Check Totals
Concept Phase | 50 | 10 |  | 0 | 0 | 50 | 10 | [6 empty] | 60
Development Phase | 100 | 20 | [5 empty] | 70 | 14 | 30 | 6 |  |  | 120
Implementation Phase | 50 | 10 | [7 empty] | 25 | 5 | 20 | 5 | 55
Construction Cost | 700 | 150 | [7 empty] | 350 | 50 | 200 | 40 | 640
Principal's Obligations | 100 | 70 | [7 empty] | 50 | 10 | 40 | 8 | 108
Finalisation Phase | 10 | 2 | [11 empty] | 0
Totals | 1010 | 262 | 0 | 0 | 0 | 50 | 10 | 70 | 14 | 455 | 71 | 260 | 53 | 983
| 1272 |  | 0 | 0 |  | 60 |  | 84 |  | 526 |  | 313 |  | 983
Converting Annual Cash Flow into 'out-turn' dollars
Enter adopted Escalation Rates % (p.a.) | [5 empty] | 3.38% |  | 3.32% |  | 2.67% |  | 2.1%
Calculated Escalation Factors |  |  |  | 1 |  | 1.0338 |  | 1.0681 |  | 1.0966 |  | 1.1197
Escalation Amounts |  |  |  | 0 | 0 | 1.69 | 0.338 | 4.7686 | 0.95371 | 43.9717 | 6.8615 | 31.1143 | 6.3425
Base Costs plus Contingency Amounts |  |  |  | 0 | 0 | 51.69 | 10.338 | 74.7686 | 14.9537 | 498.9717 | 77.8615 | 291.1143 | 59.3425
Annual Cash Flow Total |  |  |  | 0 |  | 62.028 |  | 89.7223 |  | 576.8332 |  | 350.4569
[12 empty] | Total Escalation Amount: | 96.0403
[12 empty] | Outturned Project Costs: | 1079.0403
# - For advice on escalation refer RIP Development Guidelines and/or Project Cost Estimating Manual.