## Sheet1
Annexure E
STRATEGIC CONTINGENCY/ RISK TABLE
(Based on Appendix B from RTA's Project Estimating Manual)
Complete cells with green shading
| Estimate Stage: | Strategic / Planning
Project Location:
Project Description:
Task/activity | Comments | Highly Confident & Reliable | Reasonably Confident & Reliable | Not Confident & Not Reliable | Adopted Contingency
Project Scope | Is it well defined? Yes V No Λ | 3% | 4% | 5% | 4%
| Is there room to vary the works? Yes Λ No V | 3% | 4% | 5% | 4%
| Are there many options? Yes Λ No V | 3% | 4% | 5% | 4%
Risks | Are there Significant Risks? Yes Λ No V
| Political, Community, Technical, Financial. | 5% | 6% | 8% | 6%
| Has a detailed Risk analysis been done? Yes V No Λ | 4% | 6% | 7% | 6%
Constructability | Has a constructability review been undertaken?
| Yes V No Λ | 3% | 4% | 5% | 4%
| Is constructability a problem? Yes Λ No V | 3% | 4% | 5% | 4%
Key Dates | Are the Project dates known? Yes V No Λ | 1% | 2% | 3% | 2%
| Is the project planned for the distant future? | 1% | 2% | 3% | 2%
Yes Λ No V
Information | Has investigation been Undertaken? Yes V No Λ | 9% | 12% | 15% | 12%
Geotechnical, Heritage, Environmental, Technical, Hydraulic
Length of the Project | Is the Project Short? Yes Λ No V | 4% | 7% | 10% | 7%
<1km Short >25km Long
| Total Contingency percentage to be adopted: |  |  |  | 55%
Notes:
No V denotes that if the answer is No, decrease contingency.
No Λ denotes that if the answer is No, increase contingency.
Yes Λ denotes that if the answer is Yes, increase contingency.
Yes V denotes that if the answer is Yes, decrease contingency.