## Sheet1
This calculator is able to convert 'current' dollars using a proposed cash flow and user-defined escalation rates to an expenditure profile in estimated 'out-turn' dollars.
Project No.: | 222/333/444 |  |  |  | Enter data in green shaded cells
Financial Year of estimated 'current'* dollars -> | 2014-15 |  | Costs to date (sunk costs) |  | 2017-18 |  | 2018-19 |  | 2019-20 |  | 2020-21 |  | 2021-22
| Estimated Component Costs (in 'current'* dollars) |  | Proposed Annual Cash Flow (in 'current'* dollars)
Estimate Component | Base Estimate ($,000) | Contingency Allowance ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Base Cash Flow ($,000) | Contingency Cash Flow ($,000) | Check Totals ($,000)
Concept Phase | 50 | 10 |  |  | 0 | 0 | 50 | 10 | [6 empty] | 60
Development Phase | 100 | 20 | [6 empty] | 70 | 14 | 30 | 6 |  |  | 120
Implementation Phase | 50 | 10 | [8 empty] | 25 | 5 | 20 | 5 | 55
Construction | 700 | 150 | [8 empty] | 350 | 50 | 200 | 40 | 640
Principal's Obligations | 100 | 70 | [8 empty] | 50 | 10 | 40 | 8 | 108
Finalisation Phase | 10 | 2 | [12 empty] | 0
Totals | 1010 | 262 | 0 | 0 | 0 | 0 | 50 | 10 | 70 | 14 | 455 | 71 | 260 | 53 | 983
| 1272 |  | 0 |  | 0 |  | 60 |  | 84 |  | 526 |  | 313 |  | 983
* - 'Current' dollars is the dollar value when the Base Estimate and Contingency Allowance were estimated.
Calculating Annual Cash Flow in 'out-turn' dollars
Enter adopted ESCALATION % (p.a.) # -> | [6 empty] | 5% |  | 5% |  | 6% |  | 6%
Escalation Factors |  |  |  |  | 1 |  | 1.05 |  | 1.1025 |  | 1.1687 |  | 1.2388
Escalation (Only) Amounts in Out-Turn $s |  |  |  |  | 0 | 0 | 2.5 | 0.5 | 7.175 | 1.435 | 76.7358 | 11.9742 | 62.0799 | 12.6548
Base & Contingency Amounts in Out-Turn $s |  |  |  |  | 0 | 0 | 52.5 | 10.5 | 77.175 | 15.435 | 531.7358 | 82.9742 | 322.0799 | 65.6548
Proposed Annual Cash Flow Totals |  |  |  |  | 0 |  | 63 |  | 92.61 |  | 614.7099 |  | 387.7347
[13 empty] | Escalation Allowance: | 175.0546
[13 empty] | Project Estimate (incl. Escalation): | 1158.0546
# - For advice on escalation refer RIP Development Guidelines and/or Project Cost Estimating Manual.