| Element | Inspectors | Administrator’s Representative | Administrator |
| --- | --- | --- | --- |
| Administrator Surveillance Plan | - Assist in preparation of Administrator Surveillance Plan | - Prepare and review Administrator Surveillance Plan | - Authorise issue of Administrator Surveillance Plan |
| Delegation of Functions | - Assist in preparation of delegation of functions - Report directly to Administrator’s Representative | - Prepare and review delegation of functions | - Authorise issue of delegation of functions |
| Meetings with Contractors | - Attend as required | - Attend monthly Site meetings - Minute monthly Site meetings and issue minutes - Chair meeting - Authorise minutes for issue | - Attend monthly Site meetings |
| Controlled Documents |  | - Issue Controlled Documents - Authorise issue of Controlled Documents - Prepare and maintain Controlled Document Register | - Overview |
| Meetings with the Principal | - Attend as required | - Attend as required | - Attend and minute meetings, issue advice to others (as necessary) |
| Survey | - Ensure all Principal supplied survey marks are established and identified by the Contractor - Report discrepancies to Administrator’s Representative | - Review and implement remedial action as necessary | - Overview |
| Contractor’s Quality Plan, Work Health and Safety Management Plan, Environmental Management Plan, Traffic Management Plans, Construction Program and Community Liaison Plan | - Receive and read approved copy of each | - Review plans in accordance with checklists - Deem suitable or unsuitable and issue advice to Contractor | - Overview |
| Construction Program | - Certify as built program details - Review Rolling Program for suitability - Review Contractor’s Lot Record - Review Lot Register details | - Review Rolling and Construction Program for completeness and correctness - Review Contractor’s Lot Record for as built program details - Certify current program status - Review and analysis - Maintain as-built program of works | - Overview |
| Procedural Audits / Field Surveillance / Product Audits | - Perform audits on quality records - Conduct field surveillance - Conduct products audits where relevant | - Finalise quality record audits and follow up - Maintain and update audit register - Audit Contractor’s Plans - Organise product auditing by external parties - Finalise product audits and follow up - Prepare strategic quality audit program - Review and implement audit program - Arrange specialist audits in accordance with audit program | - Overview - Authorise strategic audit program as part of Administrator’s Surveillance Plan |
| Corrective Action Requests | - Identify / investigate as requested - Prepare and maintain CAR register - Notify Administrator’s Representative | - Collate information relating to the Corrective Action Requests - Establish contractual basis for CAR and reference appropriate Contract condition - Prepare and issue CAR | - Overview |
| Principal’s Materials / Works | - Perform inspections / surveillance - Assist contractor in dealing with public utilities services - Arrange inspection of electrical works for lighting and traffic signals | - Coordinate and liaise with external parties for Principal’s Materials / Works - Review programming of Principal’s Materials / Works | - Overview |
| Contractor’s Requests for Information | - Gather information as requested | - Collate information relating to RFIs - Prepare and issue response to RFIs | - Overview |
| Design Review Requests | - Investigate / gather information as requested | - Collate information relating to DRR - Prepare DRR review and issue - Prepare and maintain DRR Register | - Overview |
| Non-conformances | - Identify and investigate / inspect, and refer to Administrator’s Representative - Sign off minor NCRs, report these to Administrator’s Representative | - Identify and clarify issues relating to the non-conformances - Maintain NCR Register - Review Non-conformance Reports for completeness - Disposition non-conformances and issue - Follow up on status of rectification works - Overview and Close Out - Refer major non-conformances to Administrator for review and issue | - Overview - Review and issue responses for major non-conformances |
| Site Inspections (Onsite and Off Site) | - Conduct daily regular inspections of the Site and adjoining road network to verify temporary signing and other traffic control devices are in place - Conduct daily inspections to verify conformity to safety and environmental requirements - Check work for conformance with the requirements of the Contract documents - Advise the Administrator’s Representative of any departures from the drawings and specifications | - Inspect critical aspects of work | - Overview |
| Hold Points | - Release Hold Points as nominated - Maintain Hold Point Register | - Monitor Hold Points release process - Release Hold Points as necessary - Review process | - Overview |
| Daily Records | - Maintain a daily record and diary of the following: - Weather conditions (including measurements) - Number of workmen - Plant onsite and in use - Materials delivered to the Site and inspection records - Any delays to the Contract and reasons - All communications with the Contractor’s foreman on the Site - Details of audit tests performed - Quality of workmanship including details of specific locations of the works - Such items as disputes, accidents or any incident considered important - Lots on which work was performed | - Maintain daily diary - Review daily reports - Maintain an onsite photographic record | - Overview |
| Contract Lot Record | - Review Contractor’s records of all lots associated with the works, which include the following: - Lot No. and description - Date lot opened and closed - Actual start date for lot - Actual completion date for lot (date work complete) - Detail of Audit types carried on lot - Lot Quantities measure by Contractor - Lot Quantities determined by Inspector - agreed measure lot quantities - Associated Schedule Item Numbers - Review Lot Register details | - Review status of Contract Lot Record | - Overview |
| Agreed Records | - Maintain agreed records with Contractor as required (Provisional / If Ordered works or other as directed) | - Review records and advise the Administrator on contractual issues | - Overview |
| Accident and Incident Reports | - Investigate and prepare draft report | - Review draft report for correctness and completeness - Amend draft report as required - Refer to the Administrator for authorisation | - Authorise report |
| Public Liaison | - Investigate / record | - Investigate and record enquiries relating to the Contract - Prepare and maintain Public Liaison Register - Investigate / record / liaise - Review responses to stakeholders - Liaise with stakeholders | - Overview |
| Site Memorandums | - Investigate / gather and collate information and draft Site Memorandum - Establish contractual basis for Site memorandum and reference appropriate Contract conditions (if applicable) - Refer to Administrator’s Representative confirmation as appropriate | - Verify contractual basis for Site memorandum - Issue correspondence with delegated authority - Review and authorise issue of memorandums | - Overview |
| Contractual Claims | - Investigate / gather information | - Collate information relating to claim - Prepare and maintain Claims Register - Assess contractual basis of claim - Review claim - Verify validity of claim - Assess quantum of claim (cost) - Prepare review and authorise response | - Overview and discuss details with Administrator’s Representative - Report potential implications to Principal |
| Variations | - Not empowered to authorise variations - Not empowered to direct / instruct the Contractor - Gather information - Maintain Agreed Records | - Identify variations - Prepare and maintain Variations Register - Collate information relating to variation - Prepare and issue Notice of Proposed Variation - Prepare, review and authorise Variation Orders | - Overview and discuss details with Superintendent’s Representative - Report potential implications to Principal |
| Under / Overs of Scheduled Quantities | - Identify future unders and over runs - Gather information of future under and over runs of scheduled quantities | - Review extent of under and over runs - Identify cost recovery if possible - Determine if alternative action is required - Prepare and issue alternative action on as necessary | - Overview and discuss details with Administrator’s Representative - Report potential implications to Principal |
| Extension of Time | - Investigate as required | - Investigate as required - Prepare and maintain Extension of Time Register - Assess contractual basis of EOT claims - Verify validity of EOT claims - Assess quantum of EOT claims (time and associated costs) - Review and authorise EOT Advice | - Overview and discuss details with Administrator’s Representative - Report potential implications to Principal |
| Progress Payments / Certificates | - Verify quantities - Review progress claim for completeness and correctness against Contract Lot Record quantities, Conformance Report, Conformance Certificate, NCRs Audits, Arithmetic, Statutory Declaration and Designer’s Certificate | - Prepare and review Progress Certificate and refer to Administrator for issue | - Overview and discuss details with Administrator’s Representative - Authorise payment certificates |
| Monthly Update of Projman |  | - Update Projman within last week of each month | - Review and overview performance |
| As Constructed Records | - Progressively maintain as-constructed records - Audit Contractor’s as built records | - Progressively review as constructed detail for completeness and correctness - Complete “As Constructed” certificate | - Overview |
| Risk Management | - Risk identification - Attend Risk Management Workshop | - Arrange Risk Management Workshop for last week of each month - Maintain Risk Register and Treatments Action Plan - Risk identification - Risk evaluation - Development of possible treatment options - Re-evaluation following implementation of possible treatment options - Forecast financial approval requirements - Establish Risk Management Program - Action planning review - Review of time, cost and quality consequences | - Review and approve risk management procedures and program - Attend and discuss details at risk management workshop - Report potential implications to Principal |