Conditions of Contract

Small Scale Minor Works

November 2023

Contents

[Conditions of Contract 1](#_Toc150262402)

[1 Definitions 1](#_Toc150262403)

[2 Execution of Works 4](#_Toc150262404)

[3 Assignment and Subcontracting 4](#_Toc150262405)

[4 Work health and safety 5](#_Toc150262406)

[5 Protection of persons and property 7](#_Toc150262407)

[6 Care of work and reinstatement of damage 7](#_Toc150262408)

[7 Indemnity by the Contractor 7](#_Toc150262409)

[8 Public liability insurance 8](#_Toc150262410)

[9 Insurance of employees 8](#_Toc150262411)

[10 Materials and workmanship 8](#_Toc150262412)

[11 Time for commencement 9](#_Toc150262413)

[12 Time for completion 9](#_Toc150262414)

[13 Defects liability period 9](#_Toc150262415)

[14 Cleaning of Site 9](#_Toc150262416)

[15 Variations 9](#_Toc150262417)

[16 Payment 10](#_Toc150262418)

[17 Default of Contractor 10](#_Toc150262419)

[18 Disputes 11](#_Toc150262420)

[19 Goods and Services Tax (GST) and Pay As You Go (PAYG) 11](#_Toc150262421)

[20 Information Privacy 12](#_Toc150262422)

[21 Anti‑competitive conduct, conflict of interest and criminal organisations 13](#_Toc150262423)

[22 Queensland Procurement Policy 13](#_Toc150262424)

[23 Records and access to records 14](#_Toc150262425)

[Annexure 16](#_Toc150262426)

[Schedules 17](#_Toc150262427)

[Schedule 1 – Request for Approval to Subcontract / Sub‑subcontract 17](#_Toc150262428)

[Schedule 2 – Subcontractor Deed Poll 19](#_Toc150262429)

# Conditions of Contract

|  |  |
| --- | --- |
| Contract Name: |  |
| Contract Number: |  |

# Definitions

1.1 In the Contract, except where the context otherwise requires, the following words and expressions shall have the meanings given to them below.

Table 1.1 - Definitions

| Term | Definition |
| --- | --- |
| Business Day | means a day that is not:   1. a Saturday or Sunday 2. a public holiday, special holiday or bank holiday in the place where the Works will be situated, or 3. a day in the period from 22 December in a particular year to 10 January in the following year, both days inclusive. |
| Contract | means the Agreement in writing between the Principal and the Contractor for the execution of the work under the Contract, including the Tender documents. |
| Contractor | means the person or company whose tender for work under the Contract has been accepted and its executors, administrators, successors or permitted assigns. |
| Date for Practical Completion | means the date, or the last day of the period of time, stated in the Annexure. |
| Defects Liability Period | means the period of time stated in the Annexure, which commences on the date that the Works reach Practical Completion. |
| [Ethical Supplier Mandate](https://www.business.qld.gov.au/running-business/marketing-sales/tendering/supply-queensland-government/ethical-supplier-requirements/mandate) | means the Queensland Government policy titled ‘Buy Queensland: Ethical Supplier Mandate’ or any policy that replaces that policy. |
| [Ethical Supplier Threshold](https://www.epw.qld.gov.au/about/strategy/buy-qld/compliance-complaints/ethical-suppliers) | means the Ethical Supplier Threshold described in the Queensland Procurement Policy. |
| Government Department or Instrumentality | means   1. any government department responsible for compliance with government policy, including without limitation: 2. the Queensland Government Procurement Compliance Branch within the Procurement Division of the Department of Energy and Public Works, or 3. the Queensland Apprenticeship and Traineeship Office within the Department of Employment, Small Business and Training. 4. Local Content with the Department of State Development, Infrastructure, Local Government and Planning, any government regulator, including without limitation: 5. the Queensland Building and Construction Commission 6. the Office of Industrial Relations Commission 7. the Fair Work Commission 8. the Australian Taxation Office 9. the Australian Building and Construction Commission, and 10. the Office of the Federal Safety Commissioner. |
| Practical Completion | means the work under the Contract is complete:   1. in accordance with the Contract, including without limitation, all plans and specifications for the Works and all statutory requirements applying to the work under the Contract, and 2. other than minor omissions and defects which will not, and the rectification of which will not, prevent or impair the normal use and occupation of the Works. |
| Principal | means the person identified as the Principal in the Annexure. |
| QGP Compliance Branch | means the State of Queensland’s Queensland Government Procurement Compliance Branch within the Department of Energy and Public Works. |
| [Queensland Procurement Policy](https://www.forgov.qld.gov.au/finance-and-procurement/procurement/procurement-resources/procurement-policies-and-frameworks/queensland-procurement-policy-2023) | means the Queensland Government policy titled ‘Queensland Procurement Policy 2023’ or any policy which replaces that policy. |
| Site | means the land and other places to be made available and any other lands and places made available to the Contractor by the Principal for the purpose of the Contract. |
| Administrator | means the person nominated by the Principal to exercise the functions of the Administrator under the Contract, who at all times must exercise its functions acting honestly and fairly, act within certain times prescribed under the Contract or where no times, a reasonable time, and arrive at a reasonable measure of value of work, quantities or time. The Administrator may appoint a representative to exercise any of its powers, duties, discretions, and authorities. |
| [Supplier Code of Conduct](https://www.forgov.qld.gov.au/finance-and-procurement/procurement/procurement-resources/search-for-procurement-policies-resources-tools-and-templates/queensland-government-supplier-code-of-conduct-2023#:~:text=The%20Queensland%20Government%20Supplier%20Code,what%20constitutes%20a%20responsible%20supplier.) | means the ‘Queensland Government Supplier Code of Conduct 2023’ or any code that replaces that code. |
| Tripartite Procurement Advisory Panel | means the panel convened under the Queensland Procurement Policy, to provide robust, independent, expert advice and recommendations to the Directors-General or other decision makers on the application of penalties under the Ethical Supplier Mandate and the Ethical Supplier Threshold. |
| work under the Contract | means all the work which the Contractor is or may be required to execute under the Contract including any variations. |
| Works | means the whole of the work to be executed and completed in accordance with the Contract, including all variations pursuant to the Contract, which is to be handed over to the Principal in accordance with the Contract. |

# Execution of Works

2.1 The Contractor must undertake the work under the Contract in accordance with the Contract, and any other documents issued by the Principal. Unless otherwise provided, the Contractor is responsible for all things, including items not expressly mentioned in the Contract, necessary for satisfactory completion of the Works. The documents forming the Contract are mutually explanatory and anything contained in one but not in another is equally binding as if contained in all.

2.2 The Contractor must comply with the requirements of all laws and public or other authorities affecting the Works and, unless otherwise specified, pay all fees, give all notices, and obtain necessary consents.

# Assignment and Subcontracting

3.1 The Contractor must not, without the prior written approval of the Principal, assign the Contract or any benefit thereunder.

3.2 The obligations of government agencies contained in the Queensland Procurement Policy will apply equally to the Contractor as though it is a government agency, and the Contractor must procure Subcontracts in accordance with the requirements of the Queensland Procurement Policy.

3.3 The Contractor must prepare and produce all required copies of the Subcontract Tender Documentation (“Subcontract Tender Documentation”), which:

1. incorporates suitable conditions of Contract which reflect the provisions of the Contract
2. requires Subcontract Tenders and Subcontractors to consent to a relevant Government Department or Instrumentality providing information to the Principal or the QGP Compliance Branch about the Tenderer’s or Subcontractor’s compliance with government policies and legislation including, without limitation, commitments made in relation to or required by the Queensland Procurement Policy, the Ethical Supplier Mandate, the Ethical Supplier Threshold, the Work Health and Safety Act 2011 (Qld) and the Electrical Safety Act 2002 (Qld)
3. requires Subcontract Tenderers and Subcontractors to acknowledge that the information referred to in Clause 3.3(b), which includes without limitation payroll records, management records and time recordings that may be held by a Government Department or Instrumentality, may be obtained by or made available to the Principal and the QGP Compliance Branch, for its information and verification of the Subcontractor Tenderer’s or Subcontractor’s compliance with commitments made in relation to or required by government policies and legislation
4. includes terms that evidence the right of the Principal and the QGC Compliance Branch to exercise the discretion in Clause 23.9 to publish any information relevant to the Ethical Supplier Mandate including, without limitation, information about the Subcontractor’s compliance with the Ethical Supplier Threshold and Ethical Supplier Mandate, and prohibits the Subcontractor from exercising any rights at law, including in Contract, at common law, or in equity, against the Principal or the Contractor in relation to that publication
5. requires the Subcontractor to execute a deed poll in favour of the Principal in the form attached to these Conditions of Contract and provide this as part of their Tender
6. requires the Subcontractor to make and keep the records referred to in Clause 23.1
7. provides for evaluation of Subcontract Tender responses against clear evaluation criteria and weightings, and
8. incorporates any other documentation or information required for the tendering or the completion of the relevant work under the Contract.

3.4 The Contractor must ensure that all Subcontractors and any sub‑Subcontractors:

1. for the purposes of the Queensland Procurement Policy are:
2. local suppliers as described in the Queensland Procurement Policy, and if a local supplier is unavailable to be sourced by the Contractor having used its best endeavours to do so, the Contractor must seek approval from the Administrator to use a supplier who is not a local supplier and in doing so must provide evidence, satisfactory to the Administrator, of its efforts to source a local supplier
3. compliant with the Ethical Supplier Threshold, and
4. not subject to a current sanction under the Ethical Supplier Mandate
5. are informed of the existence of the Building Industry Fairness (Security of Payment) Act 2017 (Qld), and
6. either:
7. have a personal services business determination in effect from the Australian Tax Office under the Income Tax Assessment Act 1997 (Cth), or
8. in relation to the work to be performed under the Subcontract (or sub‑Subcontract):
9. will be paid to achieve a specified result or outcome
10. are required to supply the plant and equipment or tools of trade needed to perform the work, and
11. will be liable for the cost of rectifying any defect in the work performed.

3.5 The Contractor must examine, analyse and evaluate all Subcontract Tenders received, in accordance with the Subcontract Tender Documentation and, in doing so, the Contractor must:

1. ensure evaluation of Subcontract Tender responses against clear evaluation criteria and weightings
2. prepare and retain written records of the evaluation process undertaken, all evaluation findings and recommendations and, if requested, submit these to the Administrator at the completion of each Subcontract evaluation.

3.6 The Contractor must not, without the prior written approval of the Administrator, which shall not unreasonably withhold, Subcontract or allow a Subcontractor to subcontract any of the work under the Contract. When seeking approval pursuant to this Clause, the Contractor must provide to the Administrator a request for approval in the form attached to these Conditions of Contract and such other information which the Administrator may reasonably request.

3.7 Within 10 Business Days after a request by the Contractor for approval made in accordance with Clause 3.6, the Administrator will approve the request or advise the Contractor of any objections. If approval is given to sub‑Subcontract part of the work under the Contract, the Contractor must ensure the requirements of Clause 3 are met.

3.8 The Principal may at any time prior to the expiration of the Defects Liability Period, undertake an audit in respect of the Contractor’s compliance with Clause 3, in accordance with the provisions of Clause 23.3.

# Work health and safety

4.1 For the purposes of this Clause:

‘Act’ means the Work Health and Safety Act 2011 (Qld)

‘Construction Project’, ‘construction work’ and ‘Principal Contractor’ have the same meanings as in the Regulation

‘inspector’, ‘notifiable incident’, ‘regulator’, ‘structure’ and ‘workplace’ have the same meanings as in the Act

‘Regulation’ means the Work Health and Safety Regulation 2011 (Qld), and

‘WHS Laws’ means the Act, the Regulation and all other applicable work health and safety legislation, regulations, rules, Codes of Practice and Australian Standards.

4.2 In relation to the work under the Contract, the Contractor will:

1. comply with and discharge all obligations imposed on the Contractor under the WHS Laws
2. unless otherwise advised in writing, accept that it is the person having management or control of the workplace at which the work under the Contract is being undertaken
3. discharge the duties of a person who conducts a business or undertaking under the WHS Laws, and
4. without limiting Clause 4.2 (a), the Contractor will ensure its officers, workers and agents, Subcontractors and its Subcontractors’ officers, workers and agents, discharge their respective duties under the WHS Laws in connection with the work under the Contract.

4.3 Where the work under the Contract comprises a construction project (that is, a project that involves construction work of $250 000 or more), from the date of acceptance of Tender:

1. the Principal engages the Contractor to be the Principal Contractor under the Regulation in relation to the construction project and authorises the Contractor to:
2. have management and control of the workplace at which the work under the Contract is being undertaken including the Site, and
3. discharge the duties of the Principal Contractor under the Regulation,
4. the Contractor accepts the engagement as Principal Contactor from the Principal and agrees to fulfil all requirements and give effect to that engagement prior to commencing any of the work under the Contract, and
5. the Contractor will comply with and discharge all obligations imposed on the Contractor, as Principal Contractor, as a person who conducts a business or undertaking and otherwise by the WHS Laws.

4.4 Without limiting any other obligations of the Contractor under the Contract, or the WHS Laws, in relation to the work under the Contract, the Contractor will:

1. consult with the Principal and consult with the designers of the whole or any part of a structure to be constructed under the Contract, about how to ensure that risks to health and safety arising from the design are eliminated during construction of the work under the Contract or, if it is not reasonably practicable to eliminate the risks, minimise the risks, so far as is reasonably practicable, and
2. in performing its obligations under the Contract, take into account and take appropriate action having regard to any information given to the Contractor by the Principal or any other person, about hazards and risks at or in the vicinity of the workplace where the work under the Contract is being carried out.

4.5 The Contractor will indemnify the Principal against any claim, action, demand, loss, damage, cost or expense which may be brought against, or suffered or incurred by, the Principal as a result of or in connection with:

1. any breach of this Clause by the Contractor
2. any breach by the Contractor of its obligations under the WHS Laws, and
3. any enforcement of obligations imposed on the Contractor under the WHS Laws.

4.6 If a notifiable incident occurs at the workplace at which the work under the Contract is being undertaken, the Contractor must:

1. immediately notify the regulator and the Administrator of the notifiable incident and provide copies of any communications, notices or reports provided to or received from the regulator or any Authority regarding the notifiable incident to the Administrator
2. take all reasonably practicable steps to secure the Site where the notifiable incident occurred, until an inspector arrives at the Site or any earlier time that an inspector directs
3. conduct a thorough investigation in relation to the root cause and contributing factors of the notifiable incident and provide a copy of the written investigation report within 10 Business Days of the Administrator's request, and
4. if the Principal wishes to conduct its own investigation, provide the Principal with reasonable assistance (including access to relevant documents and the Contractor's personnel) in investigating any such notifiable incident.

4.7 Without limiting any other obligation of the Contractor under the Contract, or the WHS Laws, if material which might contain asbestos or other hazardous substance is discovered, the Contractor must:

1. immediately notify the Administrator, and
2. comply with all applicable obligations and restrictions imposed by the WHS Laws.

# Protection of persons and property

5.1 The Contractor must:

1. take all measures necessary to protect people and property, including the Works, avoid unnecessary interference with passage of people and vehicles, prevent nuisance, unreasonable noise, and disturbance, and
2. for the purposes of Clause 5 1 (a), comply with all reasonable directions of the Administrator.

5.2 If the Contractor damages any property, the Contractor must provide temporary protection for, and repair it at its cost.

# Care of work and reinstatement of damage

6.1 The Contractor will be responsible for the care of work under the Contract.

6.2 If loss or damage occurs to the work under the Contract, the Contractor must at the Contractor’s cost rectify such loss or damage, except loss or damage caused by the negligent act or omission of the Principal, or employees or agents of the Principal.

# Indemnity by the Contractor

The Contractor indemnifies the Principal against:

1. loss of or damage to the Works or the Principal’s property, and
2. claims by any person in respect of injury, death or loss of or damage to any property,

resulting from or in any way connected with the Contractor carrying out the work under the Contract, but the Contractor’s liability to indemnify the Principal will be reduced proportionally to the extent that an act or omission of the Principal, or its employees or agents, contributed to the loss, damage, death or injury.

# Public liability insurance

8.1 Before the Contractor commences work, the Contractor shall take out a public liability policy of insurance in the joint names of the Principal and the Contractor, which covers the Principal, the Contractor, the Administrator and all Subcontractors for their respective rights and interests and covers their liabilities to third parties. The policy shall also cover the Contractor's liability to the Principal and Principal's liability to the Contractor for loss of or damage to property (other than property required to be insured) and the death of or injury to any person (other than liability which is required by law to be insured under a worker’s compensation policy of insurance). The Contractor must maintain the insurance policies required by this Clause for the duration of the Contract and produce evidence of insurance, if requested.

8.2 The public liability policy of insurance shall be for an amount in respect of any one occurrence not less than the sum stated in the Annexure and, unless otherwise specified elsewhere in the Contract, shall be effected with an insurer and in terms both approved in writing by the Principal, which may be given or withheld in its absolute discretion. The policy shall be maintained until the Practical Completion is reached.

# Insurance of employees

Before commencing the work under the Contract, the Contractor must have insurance of persons employed by the Contractor. Where the Contractor is a self‑employed person, the Contractor must maintain an equivalent insurance policy for itself. The Contractor must maintain such insurance for the duration of the Contract and produce evidence of insurance, if requested. The Contractor must ensure that every Subcontractor is similarly insured.

# Materials and workmanship

10.1 For the purposes of this Clause, ‘Non-Conforming Building Product’ has the same meaning as in section 74AB(2) of the Queensland Building and Construction Commission Act 1991 (Qld).

10.2 All materials used in any work under the Contract and the standards of workmanship must be in conformity with the provisions of the Contract. In the absence of such provisions in the Contract, the material or standard of workmanship, as the case may be, must be of a kind which is suitable for its purpose and is consistent with the nature and character of the Works. Unless otherwise specified, all materials must be new and workmanship must be in accordance with the relevant manufacturer's recommendations or, if none, the relevant Australian Standard where applicable.

10.3 The Contractor must:

1. ensure that none of the materials, plant, machinery, equipment, or products used in the Works are a Non-Conforming Building Product, and
2. promptly notify the Principal if it becomes aware, or reasonably suspects, that any materials, plant machinery, equipment, or products it has used for incorporation into the Works are a Non‑Conforming Building Project for that particular use.

10.4 Apart from any tests specified, the Administrator may, at any time, direct that any materials or work must be examined and/or tested and if necessary, rectified or replaced.

10.5 The Contractor must comply with any written direction by the Administrator to remedy any work not in accordance with the Contract, including but not limited to, defective work, loss or damage to work under the Contract and cleaning of the Site, within the period of time stated in writing by the Administrator. If the Contractor fails to comply with such a direction to carry out rectification work within the time stated, the Principal may have the rectification work, the subject of the direction, carried out by others at the Contractor’s expense or may accept the work at a reduced value.

The Principal may deduct the cost of rectification work or reduced value from payments or recover the cost or reduced value as a debt due from the Contractor. The Principal may deduct the estimated cost of rectification work from payments until such time as the Principal has incurred the cost of rectification.

# Time for commencement

The Contractor must commence the work under the Contract within the time stated in the Annexure and must, unless otherwise permitted, give at least two Business Days’ notice to the Administrator prior to the commencement of work.

# Time for completion

12.1 The Contractor must execute the Works to Practical Completion by the Date for Practical Completion or within any extended time agreed in writing by the Administrator.

12.2 When it becomes evident to a party that anything, including the act or omission of the Principal, or employees or agents of the Principal, has or will delay the work under the Contract, the party must promptly notify the Administrator in writing with details of the delay and the cause.

12.3 The Contractor is not entitled to an extension of time for delays caused by it, whether occurring before or after the Date for Practical Completion, nor for delays due to inclement weather or industrial conditions occurring after the Date for Practical Completion.

12.4 In determining a reasonable extension of time for an event causing delay, the Administrator must have regard to whether the Contractor has taken all reasonable steps to preclude the occurrence of the cause and minimise the consequences of the delay.

12.5 The Administrator may extend the Date for Practical Completion for any reason but is not obliged to exercise this right for the benefit of the Contractor.

12.6 Except where such a claim is expressly permitted in other provisions of this Contract, the Contractor will not be entitled to any additional payment because of the granting of an extension of time.

# Defects liability period

The Contractor must promptly rectify all defects and omissions notified to the Contractor during the Defects Liability Period. If the Contractor fails to do so, the Principal may have the omission or defect remedied by other persons and the cost so incurred will be a debt due to the Principal, which may be deducted from payments or recovered by any other means.

# Cleaning of Site

The Contractor must keep the Site and the Works clean and tidy and regularly remove from the Site rubbish and surplus material arising from the execution of the work under the Contract. On completion of the Works, the Contractor must clear away and remove from the Site all constructional plant, surplus materials, rubbish and temporary Works of every kind.

# Variations

The Administrator may direct in writing a variation to any work under the Contract and the Contractor must promptly comply with that direction. The Contractor must submit to the Administrator a detailed price for the variation within 10 Business Days of the direction. The variation will be valued by agreement between the Contractor and the Administrator or, failing agreement, by the Administrator and the Contract sum adjusted accordingly. The valuation will include an amount for the Contractor’s profit and attendance of 12.5 per cent. No payment for additional work will be made unless the additional work is authorised in writing by the Administrator.

# Payment

16.1. At the times stated in the Annexure, upon Practical Completion, and upon the expiration of the Defects Liability Period, the Contractor may give the Administrator a detailed payment claim supported by information the Administrator may reasonably require.

16.2. Within 10 Business Days after receipt of a payment claim, the Administrator will assess the claim and, if the Administrator determines that the amount to be paid is different to the claimed amount, will issue a payment certificate stating the amount of the payment to be made by the Principal or the Contractor and the reasons for the difference from the claimed amount.

16.3. Subject to the Contract, payment will be made within 20 Business Days of receipt of a valid payment claim.

16.4. Payment of moneys to the Contractor will not be evidence of the value of work or an admission of liability or evidence that work has been executed satisfactorily but will be a payment on account only. The Administrator may, by a later payment certificate, correct an error in a previous payment certificate. Nothing in the Contract will oblige the Principal to pay for work that is not in accordance with the Contract, or for plant or materials not incorporated in the Works on the Site.

16.5. For the purposes of the *Building Industry Fairness (Security of Payment) Act*2017 (Qld), the Administrator is authorised to receive payment claims and to issue payment schedules on behalf of the Principal. For your information, the payment certificate under the Contract is deemed to be the same as the payment schedule under the Act.

16.6. Payment will take into account the deduction of retention monies (if any) and any other amount which the Principal may be entitled to deduct or which is due and payable by the Contractor to the Principal whether under the Contract, any other Contract, or independent of Contract. If the moneys to be deducted are insufficient to discharge the liability of the Contractor, the Principal may have recourse to retention moneys or unconditional undertakings provided in lieu of retention.

16.7. The Principal’s entitlement to retention moneys (if any) will be reduced to the percentage stated in the Annexure when the Contractor has achieved Practical Completion as certified by the Administrator.

# Default of Contractor

17.1 Subject to Clause 17.3, if the Contractor:

1. fails to commence the work under the Contract within the time for commencement stated in the Annexure, or
2. fails to proceed with the work under the Contract at a reasonable rate of progress, or
3. commits any substantial breach of the Contract,
4. the Principal may, by written notice, require the Contractor to show cause by the date stated in the notice, why the Principal should not exercise a right under Clause 17.2 (Show Cause Notice)

17.2 If the Contractor fails to show reasonable cause by the date stated by the Principal in the Show Cause Notice, then the Principal will have the power upon notice, in writing, to the Contractor to:

1. terminate the Contract, or
2. suspend payment and take the work remaining to be completed wholly or partly out of the hands of the Contractor,

without prejudice to any rights of the Principal under the Contract or at common law.

17.3 If the Contractor:

1. fails to hold or maintain a current licence, if required, to perform the work under the Contract
2. becomes insolvent or bankrupt, or being a company goes into liquidation, or takes or has instituted against it any action or proceedings which has as an object or may result in bankruptcy or liquidation
3. enters into a debt agreement, a deed of assignment, or a deed of arrangement under the Bankruptcy Act 1966 (Cth), or, being a company, enters into a deed of company arrangement with its creditors, or an administrator or controller is appointed, or
4. has a receiver or a receiver and manager appointed, or a mortgagee goes into possession of any of its assets,

the Principal may, without giving a Show Cause Notice, exercise a right under Clause 17.2

17.4 In the event that the Principal takes the work out of the hands of the Contractor, the Principal may itself or by means of other persons, complete the whole or any part of that work and may without payment of compensation take possession of the constructional plant and other things on or in the vicinity of the Site that are owned by the Contractor. If the cost incurred by the Principal in completing the work is greater than the amount which would have been paid to the Contractor if the Contractor had completed the work, the difference will be a debt due from the Contractor to the Principal, otherwise any difference will be a debt due from the Principal to the Contractor.

# Disputes

Within 10 Business Days of a dispute arising, either party may refer it to the Administrator. Within 20 Business Days of receiving notice of dispute, the Administrator will give its written decision to each party. If the Administrator fails to give the decision, or if either party is dissatisfied with it, the parties must within 10 Business Days of receipt of the decision, or the date upon which it should have been given, confer at least once to attempt to resolve the dispute.

# Goods and Services Tax (GST) and Pay As You Go (PAYG)

19.1 Definitions

For the purposes of this Clause:

‘ABN’, ‘adjustment event’, ‘adjustment note’, ‘amount’, ‘Australian resident’, ‘consideration’, ‘GST’, ‘GST Law’, ‘input tax credit’, ‘recipient created tax invoice’, ‘registered’, ‘tax invoice’, ‘taxable supply’ have the same meanings as in the A New Tax System (Goods and Services Tax) Act 1999 (Cth).

19.2. GST Included in Price

Payments for any taxable supplies under the Contract include GST.

19.3. Tax Invoices

Alternative 1\*

The Contractor must issue to the Principal, a tax invoice or adjustment note (as the case may require) within five Business Days after each of the following occurring in relation to that taxable supply:

1. the Contractor submitting a claim for payment that is not in the form of a valid tax invoice
2. the Administrator certifying an amount for payment different to the amount claimed, and/or
3. the amount for payment being otherwise determined to be different to the amount claimed or (if applicable) certified.

19.4 PAYG Withholding

Whenever the Principal reasonably considers itself bound by law to do so, the Principal will be entitled to withhold from any payment otherwise due to the Contractor, amounts calculated and to be withheld in accordance with the law.

# Information Privacy

For the purposes of this Clause:

20.1 ‘Personal Information’ means information or an opinion, including information or an opinion forming part of a database, whether true or not and whether recorded in a material form or not, about an individual whose identity is apparent or can reasonably be ascertained, from the information or opinion.

20.2 If the Contractor collects or has access to Personal Information to carry out work under the Contract, the Contractor must:

1. if the Principal is an ‘agency’ within the meaning of the Information Privacy Act 2009 (Qld) (“IPA”), comply with Parts 1 and 3 of Chapter 2 of the IPA in relation to the discharge of its obligations under the Contract as if the Contractor was the Principal
2. not use Personal Information other than in connection with carrying out work under the Contract, unless required or authorised by law
3. not disclose, or transfer outside of Australia, Personal Information without the prior written consent of the Principal, unless required or authorised by law
4. ensure that its officers, employees, agents and Subcontractors do not access, use or disclose Personal Information other than in connection with carrying out work under the Contract
5. ensure that its Subcontractors who have access to Personal Information comply with obligations the same as those imposed on the Contractor under this Clause
6. fully co-operate with the Principal to enable the Principal to respond to applications for access to, or amendment of a document containing an individual’s Personal Information and to privacy complaints, and
7. comply with such other privacy and security measures as the Principal may reasonably require from time to time.

20.3 On request by the Principal, the Contractor must obtain from its employees, officers, agents or Subcontractors carrying out work under the Contract, an executed deed of privacy in a form acceptable to the Principal.

20.4 The Contractor must immediately notify the Principal on becoming aware of any breach of this Clause.

20.5 The Contractor acknowledges that, in accordance with the Contract, the Administrator, the Principal and the QGP Compliance Branch:

1. will collect information for the purposes of administering the Contract that may contain Personal Information which will be used in accordance with the Contract and may be disclosed to the Administrator, the Principal, the QGP Compliance Branch and agents, consultants, or other Contractors engaged by the Principal, but will not be disclosed to any other third party without the Contractor’s consent unless authorised or required by law or the Contract, and
2. may collect information containing Personal Information for the purposes of determining the Contractor’s compliance with the Ethical Supplier Threshold and the Ethical Supplier Mandate which may be disclosed to the Tripartite Procurement Advisory Panel for compliance purposes but will not be disclosed to any other third party without the Contractor’s consent unless authorised or required by law or in the Contract.

20.6 Personal Information will be handled in accordance with the IPA.

20.7 This Clause will survive the termination or expiry of the Contract.

# Anti‑competitive conduct, conflict of interest and criminal organisations

21.1 For the purposes of this Clause:

‘Personnel’ means officers, directors, employees, agents and Subcontractors, and

‘Conflict of Interest’ includes any actual, reasonably anticipated or perceived Conflict of Interest, whether personal, financial, professional or otherwise.

21.2 The Contractor warrants that neither it, nor its Personnel have engaged in, or will engage in, any collusive, anti‑competitive or similar conduct in connection with the Contract, any associated Tender or any actual or potential Contract with any entity for the Works. In addition to any other remedies available to it under law or Contract, the Principal may, in its absolute discretion, immediately terminate the Contract if it believes the Contractor has engaged in collusive or anti‑competitive conduct. The Contractor warrants that it and its Personnel do not hold any office or possess any property, are not engaged in any business or activity and do not have any obligations where a Conflict of Interest is created, or might appear to be created, in conflict with its obligations under the Contract, except as disclosed. If the Principal requests, the Contractor must obtain from its Personnel a signed Conflict of Interest declaration in a form acceptable to the Principal.

21.3 The Contractor warrants that neither it nor its Personnel have been convicted of an offence where one of the elements of the offence is that the person is a participant in a criminal organisation within the meaning of section 161P of the Penalties and Sentences Act 1992 (Qld).

21.4 The warranties in this Clause are provided as at the date of the Contract and on an ongoing basis. The Contractor warrants that it will immediately notify the Principal if it becomes aware that any warranty made in this Clause was inaccurate, incomplete, out of date or misleading in any way when made, or becomes inaccurate, incomplete, out of date or misleading in any way.

21.5 In addition to any other remedies available to it under law or Contract, the Principal may, in its absolute discretion, immediately terminate the Contract if it believes the Contractor has breached any warranty in this Clause.

# Queensland Procurement Policy

22.1 The Contractor must, and must ensure its Subcontractors, in carrying out the work under the Contract, comply with:

1. the principles of the Queensland Procurement Policy and any requirements under the Contract in this regard
2. the Ethical Supplier Threshold
3. the Ethical Supplier Mandate, and
4. the Supplier Code of Conduct.

22.2 The Contractor acknowledges that a failure to comply with government policies and legislation that apply to the work under the Contract or the Contractor’s obligations under the Contract can result in the imposition of a penalty under the Ethical Supplier Mandate, in addition to any other remedies available to the Principal under the Contract.

22.3 The Contractor:

1. consents to a relevant Government Department or Instrumentality providing information to the Principal and the QGP Compliance Branch, and
2. authorises the Principal and the QGP Compliance Branch to obtain information about the Contractor’s compliance with government policy and legislation, including without limitation the Queensland Procurement Policy, the Ethical Supplier Threshold, the Ethical Supplier Mandate, the Supplier Code of Conduct, the Work Health and Safety Act 2011 (Qld) and the Electrical Safety Act 2022 (Qld).

22.4 Failure to comply in any respect with the requirements of the Queensland Procurement Policy will be considered a substantial breach of the Contract.

# Records and access to records

23.1 The Contractor must make and keep and must ensure that every Subcontractor makes and keeps accurate and complete records of:

1. the Contractor’s or Subcontractor’s Tender, including without limitation the preparation and submission of that Tender
2. Tenders received by it, whether accepted or not
3. the execution and completion of the work under the Contract, or of the work under the Subcontract, and
4. compliance with commitments made in the Contractor’s Tender relating to or required by government policies including but not limited to the Queensland Procurement Policy, the Ethical Supplier Threshold and the Ethical Supplier Mandate and the Supplier Code of Conduct including, without limitation, payroll records, management records and time recordings, and
5. are in a format or stored on any medium including, without limitation, photographs, electronic files, telecommunications or social media.

23.2 The records referred to in Clause 23.1 must not be destroyed without the prior written approval of the Principal.

23.3 Without limiting any other rights or obligations under this Clause, the Principal and the QGP Compliance Branch may, at any time after giving written notice to the Contractor that an audit will be undertaken pursuant to this Clause 23.3, undertake an audit in respect of the Contractor’s compliance with Clause 3. In undertaking the audit, the Principal and the QGP Compliance Branch will have the right to inspect and copy any record referred to in Clause 23.1 and to access any of the Contractor’s systems and processes which are in any way connected to Subcontracting. Upon receipt of written notice of the audit pursuant to this Clause 23.3, the Contractor must promptly and, at its own cost, provide the Principal and the QGP Compliance Branch with every reasonable facility necessary to undertake the audit, including but not limited to:

1. providing to the Principal and the QGP Compliance Branch any record requested for inspection or copying pursuant to Clause 23.5
2. making staff available to the Principal and the QGP Compliance Branch to access or explain systems, processes, or any record referred to in Clause 23.1, and
3. arranging and providing access to the Contractor’s or Subcontractor’s workplaces, sites, premises, or facilities.

23.4 Subject to the Contractor’s right to claim legal professional privilege in respect of any record, which is hereby maintained, the Principal and the QGP Compliance Branch will have the right to inspect and to copy at any time any record referred to in Clause 23.1. In the case of any records referred to in Clause 23.1 stored on a medium other than in writing, the Contractor must make available forthwith upon request such facilities as may be necessary to enable a legible reproduction thereof to be provided to the Principal and the QGP Compliance Branch.

23.5 Where a record referred to in Clause 23.1 is created, maintained or stored by a Contractor or a Subcontractor in an electronic format, it must be provided to the Principal in its native, operable form or such other format as may be reasonably required by or acceptable to the Principal.

23.6 Where a record referred to in Clause 23.1 is stored on a medium licenced from a third party, where the Principal is a party to the communication, the Contractor must provide the Principal with a copy of such records in an external electronic storage device, readable on the Principal’s information technology system, or such other format as may be reasonably required by the Principal, each month until the expiration of the Defects Liability Period.

23.7 The Contractor must comply in all respects with any request made pursuant to Clause 23.5 to inspect or copy records referred to in Clause 23.1, or any audit undertaken pursuant to Clause 23.4. and will not be entitled to refuse audit, inspection or copying of any record referred to in Clause 23.1 on any basis whatsoever other than on the basis that legal professional privilege attaches to the record.

23.8 Records accessed under Clauses 23.4 or 23.5 may be used to assess the Contractor’s or its Subcontractors’ compliance with the Contract, the Subcontract, the Queensland Procurement Policy, Ethical Supplier Threshold, the Ethical Supplier Mandate and the Supplier Code of Conduct and may be shared with relevant Government Departments or Instrumentalities for the purposes of the making of a recommendation about compliance with the Queensland Procurement Policy, Ethical Supplier Threshold, the Ethical Supplier Mandate and the Supplier Code of Conduct.

23.9 The Principal and the QGP Compliance Branch may in their absolute discretion, publish information about the Contractor’s or a Subcontractor’s compliance with the Ethical Supplier Mandate, including but not limited to any sanctions or penalties imposed, and the parties acknowledge and agree that, to do so, will not constitute a breach of this Contract by the Principal, nor give rise to any other right or remedy of the Contractor at law or in equity against the Principal or the QGP Compliance Branch.

Annexure

|  |  |  |
| --- | --- | --- |
| Item |  |  |
|  | The Principal (Clause 1): | The State of Queensland acting through the Department of Transport and Main Roads |
|  | The address of the Principal: |  |
|  | The Administrator (Clause 1): | As per Letter of Acceptance |
|  | The address of the Administrator: | As per Letter of Acceptance |
|  | Address of the Site (Clause 1): |  |
|  | Amount of public liability insurance shall not be less than (Clause 8): | [ $ Type here.  If nothing stated, amount is $20 000 000 ] |
|  | Time for commencement (Clause 11): | \*within ……Business Days of acceptance or \*…/…/20…  (\*Delete one) |
|  | Date for Practical Completion (Clause 12): | \*within ……weeks from acceptance or \*…/…/20…  (\*Delete one) |
|  | Defects Liability Period (from Practical Completion) (Clause 13): | (If nothing stated – six months) |
|  | Time for making payment claims (Clause 16): | Last Business Day of the month  (If nothing stated – Monthly) |
|  | Retention moneys deducted from progress payments (Clause 16): | 10% of the value of work completed (excl. GST) until 5% of the Contract sum (excl. GST) is held |
|  | Retention moneys held after Practical Completion (Clause 16): | 2.5% of the Contract sum (excl. GST) |
|  | GST and PAYG (Clause 19): | Alternative 1 |

Schedules

Schedule 1 – Request for Approval to Subcontract / Sub‑subcontract

(Clause 3)

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Name: | |  | | | | | |
| Contract Number: | |  | | | | | |
| Pursuant to Clause 3 of the Conditions of Contract I request approval to enter into a Subcontract for the following part of the work under the Contract: | | | | | | | |
| Proposed Subcontractor: | | |  | | | | |
| ACN: |  | | | | ABN: | |  |
| Address: |  | | | | | | |
| Licence No: |  | | | | | Category: |  |
| Trade: |  | | | | | Restrictions (if any): |  |
| Total value of proposed Subcontract: | | | | $ | | | |

I confirm that the proposed Subcontractor:

1. is:

☐ a local supplier as described by the Queensland Procurement Policy, or

☐ not a local supplier as described by the Queensland Procurement Policy and evidence is attached demonstrating the Contractor’s efforts to source a local supplier, and

1. is compliant with the Ethical Supplier Threshold
2. is not subject to a current sanction under the Ethical Supplier Mandate
3. has been informed of the existence of the Building Industry Fairness (Security of Payment) Act 2017 (Qld), and
4. either:
   1. has a personal services business determination in effect from the Australian Taxation Office under the *Income Tax Assessment Act* 1997 (Cth), or
   2. in relation to the work to be performed under the Subcontract:
      1. will be paid to achieve a specified result or outcome
      2. is required to supply the plant and equipment or tools of trade needed to perform the work, and
      3. will be liable for the cost of rectifying any defect in the work performed.

I warrant that if approval is granted, the Subcontract will be entered into in accordance with the above.

|  |  |
| --- | --- |
| Signed |  |
| Date | …/…/…… |

Schedule 2 – Subcontractor Deed Poll

(Clause 3)

FORM OF DEED POLL

THIS DEED POLL is made at ………………… on the ……day of ………… 20……

BY ……………………...……………………………………………………… (ABN ………………………….) of …………………………………………………………………………………… (the “Subcontractor”).

IN FAVOUR OF: The State of Queensland through …………………………………………………………………………. …………………………………………………………………………………………………………………..(hereinafter with its successors in office, nominated agents and the Queensland Government Procurement Compliance Branch (“QGP Compliance Branch”) called the “Principal”).

*RECITALS*

1. The Principal has entered into an agreement with: ……………………………………………….…………… (the “Contractor”) for the ………………………………………………………………………... (the “Project”).
2. The Subcontractor has or will have an agreement (the “Subcontract”) with the Contractor or a Subcontractor of the Contractor for the execution and completion and/or supply of the …………………………...……………. (the “Subcontract Works”) for the Project.
3. It is or will be a condition of the Subcontract that the Subcontractor executes this Deed Poll.

This Deed Poll provides as follows:

1. The Subcontractor warrants that:
   1. it will make and keep accurate and complete records of:
      1. its Tender, including without limitation the preparation and submission of that Tender
      2. Tenders received by it, whether accepted or not
      3. the execution and completion of the work under the Subcontract, and
      4. compliance with any commitments made in the Subcontractor’s Tender and its obligations under the Subcontract relating to compliance with government policies including but not limited to the Queensland Procurement Policy, the Ethical Supplier Mandate and the Ethical Supplier Threshold,

the records referred to in Clause 1(a) above must include records that are required to be created or provided, or that are otherwise referred to, under the Subcontract, as well as other records including but not limited to those that:

* + 1. relate to the Subcontractor’s Tender, including Tender preparation, submission, negotiation, evaluation, estimates and calculations
    2. relate to design, including design calculations, option studies, opinions, reviews, and reports
    3. relate to the execution and completion of the work under the Subcontract, including without limitation labour, Subcontracts, Subcontractors, consultants, materials, equipment, resourcing, planning, progress, delay, inspection, examination, testing, compliance, approval, safety, risk, variations, claims, payment, cost and cost to complete
    4. are required to demonstrate compliance with the matters referred to in Clause 1(a)(iv) above, including without limitation payroll records, management records and time recordings, and
    5. are in a format or stored on any medium including, without limitation, photographs, electronic files, telecommunications, or social media,

subject to the Subcontractor’s right to claim legal professional privilege in respect of any record, which is hereby maintained, permit the Principal and the QGP Compliance Branch to inspect and to copy at any time any records referred to in Clause 1(a) or 1(b) above, provide electronic copies of such records in native format and provide any access to the Subcontractor's sites, premises, or facilities necessary for an inspection referred to in this paragraph

without limiting the previous paragraphs, the Subcontractor will permit the Principal and the QGP Compliance Branch to undertake an audit of the records referred to in Clause 1(a) or 1(b) above for the purposes of verifying the Subcontractor’s compliance with any commitments made in the Subcontractor’s Tender and its obligations under the Subcontract relating to compliance with government policies including the Queensland Procurement Policy, the Ethical Supplier Mandate and the Ethical Supplier Threshold.

1. The Subcontractor consents to the Principal and the QGP Compliance Branch disclosing or providing copies of any records which the Principal and the QGP Compliance Branch inspects or copies in accordance with Clause 1 of this Deed Poll to the Contractor.
2. The Subcontractor consents to the Principal and the QGP Compliance Branch, in its absolute discretion, publishing information about the Subcontractor’s compliance with the Ethical Supplier Mandate, including but not limited to any sanctions or penalties imposed, and warrants that it will not exercise any right at law, including in Contract, at common law or in equity, against the Principal, including the QGP Compliance Branch, in relation to that publication.
3. This Deed Poll is governed by and construed in accordance with the laws of Queensland. The Subcontractor hereby submits to the non‑exclusive jurisdiction of the courts of Queensland and any courts that may hear appeals from any of those courts, for any proceedings in connection with this Deed Poll, and waives any right it might have to claim that those courts are an inconvenient forum.

This Deed Poll may not be revoked or otherwise modified without the prior written consent of the Principal.

**EXECUTED as a DEED POLL**

on the ……day of ……… 20…… by

|  |  |
| --- | --- |
|  |  |
| *Name of Company – Subcontractor* | *ACN* |

in accordance with s 127 of the *Corporations Act* 2001 (Cth)

|  |  |
| --- | --- |
|  |  |
| *Name of Director* | *Signature of Director* |
|  |  |
| *Name of Director / Secretary* | *Signature of Director / Secretary* |

OR

|  |  |
| --- | --- |
|  |  |
| *Name of Person – Subcontractor* | *Signature of Person – Subcontractor* |

In the presence of:

|  |  |
| --- | --- |
|  |  |
| *Name of Witness* | *Signature of Witness* |