## Implementation Plan-C6089
Implementation Plan for Evidence Guide
RMPC
C6089
All requirements stated herein are minimum requirements to be met by the Contractor as an alternative to compliance with ISO 9001, only where this alternative method of compliance has been agreed to between the parties, in writing, at the commencement of the Contract. These requirements are to be categorised according to their level of risk as assessed by the parties on a case by case basis to reach mutual agreement. The agreed requirements shall at all times be complied with by the Contractor in accordance with the following legend:
Mandatory (M) these minimum mandatory requirements are considered high risk and must be complied with accordingly. Non-compliance shall constitute a breach unless specifically excepted in writing, following consultation between the parties on a case by case basis. Where compliance with state minimum requirements has been so excepted, the Contractor must take documented steps to prioritise and implement the requirements in accordance with the terms contained in the written varied requirement and within the time stated therein.
Desirable (D) these minimum mandatory requirements are considered lower risk and the Contract parties shall, prior to the commencement of the works, evaluate the risk of these requirements and shall agree in writing on the action accordingly required. Where the risk is assessed as high, the Contractor shall address the requirement as mandatory and shall accordingly be subject to the same requirements, and follow the same processes as required under (M). Where the risk is assessed as lower than that assessed under (M), the action agreed must at all times be commensurate with the risk of the requirement as assessed by the parties and must be implemented within the timeframe agreed upon. The parties must assess the risk as required throughout the Contract as risks may change from time to time depending on the works being carried out in the Contract.
Optional (O) these minimum mandatory requirements are considered low risk and may be addressed accordingly following similar consultation as required under (D).
ISO 9001 Elements | Evidence Guide | Priority | Has the Contractor agreed to Implement on commencement (Yes/No)? | If No, provide reasons | Provide new timeframe/milestones agreed upon with the Contractor for Implementation (with any comments)
4.2.2 QA Manual | Organisational structure for RMPC works | M
| Quality policy/statement | M
| Roles/Responsibilities/Accountabilities for RMPC works | M
| Simple RMPC map/diagram | O
| Cross-reference table of RMPC doc's detailing ISO 9001 requirements | O
| Supporting check lists/procedures/forms | M
4.2.3 Control of Documents | RMPC documents and specifications (for example, signed documents, drawings approved for Minor Works, manuals) | M
| Document distribution controlled | M
| Reference library list/web sites used | D
| Control on obsolete documents (as required) | D
| Circulation of communication/updates to all | D
| Removal of obsolete documents | D
| Access to technical data | D
4.2.4 Control of Records | Records of various inspections including complaints/defects/road-runs | M
| Program of works | M
| Contract variations & correspondence | M
| Test records when required (for example, material supply) | M
| Records of meetings for example, focus meeting, toolbox talks, team meeting, quality committee, pre-start meeting, monthly meeting, and post construction meeting, and so on | M
| Register of Issues for example, complaints and feedback | M
| Job related records (for example, work orders, completed works) See 7.5 | M
| IT backups, tapes, CDs, Backup reports, and so on | D
5.0 Management Responsibility | Council's Network obligation, maintenance manager and supervisor and operations contractor – as defined in Part 3 of RMPC General Conditions of Contract – Volume 1 | M
| Business/Operational Plan | O
| Review of objectives/KPIs of Council | D
| Roles and responsibilities are defined in the Project Quality Plan | M
| Minutes of Management Review | M
6.2.2 Competence Awareness & Training | Competent and appropriately skilled people carry out RMPC works | M
| Maintained appropriate records of education, training, skills and experience for RMPC works | M
6.3 Plant & Equipment | Appropriately maintained infrastructures | D
6.4 Work Environment | Suitable work environment for example, "Safe Plan" scheme includes Site Inductions, safety committee, PPE, track attenuators, and so on | M
7.1 Planning of Product Realisation (Planning the work) | Project quality system plans are interconnected with addresses:
| Quality (for example, 8.2.4) | M
| Safety including Traffic Management | M
| Environmental Management | M
| Emergency Response | M
| Communication | M
| Network inspection schedule | M
7.1 Planning of Product Realisation (Planning the work) | Activity Standards | M
| Planning prior to agreement | M
| Reaching agreement | M
7.2 Customer Related Process (Contract Review) | Contract Performance Report | M
| Minutes of Meetings | M
| Update relevant documentation | M
| Subsequent changes are maintained and controlled | M
7.3 Design & Development | Evidence of approved design (for example, seal design, pavement design, and so on) | M
7.4 Purchasing | Proof of approved suppliers used and materials used | D
7.5 Product & Service Provision (Doing the work) | List of prioritised work in the road network | M
| Records of defects matched to Invention Levels (backlog report) | M
| Activity standards for undertaking maintenance | M
| Work instruction/forms used/procedures to manage work | M
| Job records (for example, works orders, test results, traffic management record, and so on) | M
| Job Diary notes/Inspection records | M
| Payment Claims | M
| Accident/Incident reports for safety and legal requirements | M
7.5.3 Identification & Traceability (Job Numbering) | Completed activity report (ASCII format) | M
| Reporting Completed Maintenance | M
| Completed works orders | M
7.5.4 Customer Property | Due care taking of departmental property (for example, materials) | M
| Records of non-conforming materials | M
7.5.5 Preservation of product | Material Safety Data Sheet (MSDS) are available | M
| Stock take results from Depot/Store | O
| "Safe Plan" Inspections | M
7.6 Calibrations of Monitoring & Measuring Practices | Records of calibration/2 peg tests for levels, theodolites, survey equipment | D
| Survey equipment maintenance schedule | D
| Maintenance/servicing records | D
| Calibration of equipment for high risk operations (for example, setting drainage lines in built-up areas) | D
8.2.1 Customer Satisfaction | Complaints/correspondence/project review minutes | M
| Issue management actions and records (for example, records, correspondence, media releases, public notices, register, and so on) | M
| Correspondence/records as appropriate | M
| Phone contacts with public/MR | M
| Rate payer survey results (if available) | O
| Accident/Incident reports | M
| Client's feedback | M
8.2.2 Internal Audit | Internal audit records – safety, quality, environmental and traffic management | M
| Internal audit action taken, reporting of results to senior managers/project managers for management review purposes | M
| Improvements made as recommended from previous audit | M
| Surveillance records and inspection records | D
| Self-checking records | D
8.2.3 Monitoring and Measurement of Process | Issues management | M
| Regular verification of processes (for example, site inspection records, meeting minutes and so on) | M
| Reporting to senior management | D
8.2.4 Monitoring and Measurement of Product | Test results/records/conformance reports/corrective action reports where necessary | M
| Completed ITPs/Hold Points approved (where required) | M
| Job Diary/Overseer records | M
8.3 Control of Non-Conforming Products | Evidence of managing non-conforming product (for example, non-conforming reports, corrective action reports and action taken) | M
| Report to senior managers/project managers | M
| Register of Corrective Actions Requests (CARs/Issues updates with action taken for close out) | M
8.4 Analysis of Data | Minutes of regularly held meetings | M
| Records from customer feedback system | M
| Data is analysed to solve recurring problems (if any) | D
| Identification of trends and cause, monitoring and improving customer satisfaction and process capability | M
| Results of data analysis are discussed in Management review meetings | D
8.5.1 Continual Improvement | Any improvement initiative including:
| Review of work practices | M
| No accidents/incidents | M
| Productivity changes | M
| Hierarchy of Control when and where required | M
8.5.2 Corrective Action | Evidence of managing non-conforming product (for example, non-conforming reports, corrective action reports and action taken) | M
| Report to senior managers/project managers | M
| Register of CARs/Issues updated with action taken for close out | M
8.5.3 Preventive Action | Evidence of managing non-conforming product (for example, non-conforming reports, correction action reports and action taken) | M
| Report to senior managers/project managers | M
| Register of CARs/Issues updated with action taken for close out | M
Agreed by Local Government Signature |  | Agreed by Transport and Main Roads Signature

## Data sheet (hidden)
Yes
No